## Sheet1
Recipe App
Bishal Heuju
Plan | Schedule (Days)
Analysis of existing similar apps | 1 | Completed
Creation of single recipe view - using hardcoded recipe data
Implementation of SQL server for retrieving recipe data from database | 1
Creation of home page to display list of recipes - using hardcoded recipe data | 1
Display recipe list in home page by retrieving through database | 1
CreateRecipe page for allowing users to create recipes and add to database | 1
Handling image upload for recipe creation
Addition of user authentication | 4 | Pending
User database addition
User sepcific features addition - favourite, create recipes | 4
Limit access based on user accounts (admin privileges)
User dashboard to allow users to view user specific details - favourited recipes | 1
UI and UX touchup | 1
20 % complete